## Start Here
MALAMAAL Execution Toolkit — Workbook
Daily → DCR ¦ Weekly → Review + KPI ¦ Monthly → Deep-dive ¦ Fill it, don't perfect it.
| Sheet | How to use
1 | Day Close Report (DCR) | Fill EVERY evening (6 PM default). One row per day. Log what got done, what's pending, and tomorrow's top 3.
2 | Weekly Review | Fill Friday evening / Monday morning. Roll up the week's DCRs. Ask: 'What moved the needle this week?'
3 | KPI Tracker | Pick 5–7 KPIs. Set targets once. Enter Actuals weekly — Variance & % calculate automatically (green = on target).
4 | Feedback Log | Capture every customer/team insight. Assign an owner. Review monthly, drive Pending → Done.
5 | Kanban Board | 3 columns: To Do / In Progress / Done. Move tasks daily. Don't let anything sit 'In Progress' forever.
| Legend: | Yellow cells = you type here. White cells with formulas calculate on their own — don't overwrite them.

## DCR
Day Close Report (DCR)
Fill every evening in under 90 seconds.
Date | Tasks Completed | Pending Tasks | New Deadline | Next Day Priorities (max 5) | Needle? Y/N
2026-08-12 | 18 sales calls made | Send Distributor Z proposal | 2026-08-13 | 1) Close 2 meetings 2) Launch ad 3) Follow up agency | Y | ← example

## Weekly Review
Weekly Review Sheet
Step back, look at the week, plan the next.
Week | Planned Goals | Achieved | Major Wins | Challenges | Next Week Focus
Wk 32 | 20 sales calls, launch ad | 18 calls, ad delayed | 2 new distributors onboarded | Vendor supply delay | Launch ad, close Distributor Z

## KPI Tracker
Performance Matrix / KPI Tracker
Set targets once. Enter Actuals weekly — Variance calculates itself.
KPI | Target | Actual | Variance (+/-) | Variance % | Remarks
Sales Calls | 20 | 18 | -2 | -10% | 2 meetings postponed
Proposals Sent | 5 | 4 | -1 | -20%
Deals Closed | 2 | 2 | 0 | 0%
Collections (₹) | 100000 | 82000 | -18000 | -18% | 2 invoices pending
Repeat Customers | 15 | 17 | 2 | 13.33% | Above target
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
Variance = Actual − Target. Variance % = (Actual−Target)/Target. Yellow = your inputs; columns D & E auto-calc.

## Feedback Log
Feedback Log
Capture insights, assign an owner, close the loop.
Date | Type | Feedback | Action Taken | Assigned To | Status
2026-08-12 | Suggestion | Add online payment option | Checking with gateway | Ops | Pending

## Kanban
Kanban Board
Move cards daily. Nothing sits 'In Progress' forever.
To Do | In Progress | Done
Client Proposal X | New Product Design | Marketing Plan